## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Hair Oil Formulation - Launch |  |  |  |  | COMPANY NAME | [6 empty] | Hair Oil Ltd
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | [6 empty] | 2025-01-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Research and Concept Development
1.1 | Market research | Monica M | 2025-01-01 | 2025-03-07 | 10 | 100% | bar: WEEK 1 M to WEEK 2 F
1.1.1 | Conduct Surveys | Kylie R | 2025-02-10 | 2025-03-07 | 5 | 100%
1.1.2 | Analyse competitor's products | Kylie R | 2025-01-20 | 2025-02-14 | 4 | 100% | bar: WEEK 1 W to WEEK 2 M
1.1.3 | Identify target audience trends | Kylie R | 2025-01-06 | 2025-02-07 | 4 | 100% | bar: WEEK 1 T to WEEK 1 F
1 | Milestone: Document with market anlysis |  |  | 2025-03-07 | bar: WEEK 2 F
1.2 | Product Conceptualization | Pete S | 2025-03-03 | 2025-04-11 | 5 | 90% | bar: WEEK 2 R to WEEK 3 W
1.2.1 | Define Key benefits of the hair oil | Pete S | 2025-03-03 | 2025-04-11 | 5 | 90% | bar: WEEK 2 R to WEEK 3 W
1.2.2 | Define type of oils and ingredients | Pete S | 2025-03-03 | 2025-04-11 | 5 | 90% | bar: WEEK 2 R to WEEK 3 W
2 | Milestone: Document with product conceptualization |  |  | 2025-04-11 | bar: WEEK 3 W
1.3 | Regulatory research | Monica M | 2025-03-24 | 2025-04-25 | 4 | 90% | bar: WEEK 3 M to WEEK 3 F
1.3.1 | Local and international regulations | Monica M | 2025-03-24 | 2025-04-18 | 4 | 90% | bar: WEEK 3 M to WEEK 3 R
1.3.2 | Label & Safety requirements | Pete S | 2025-03-31 | 2025-04-25 | 4 | 90% | bar: WEEK 3 T to WEEK 3 F
3 | Milestone: Document about regulations |  |  | 2025-04-25 | bar: WEEK 3 F
2 | Formulation and testing
2.1 | Ingredient Sourcing | Steve L | 2025-04-18 | 2025-06-09 | 7 | 90% | bar: WEEK 3 R to WEEK 4 F
2.1.1 | Identify suppliers | Monica M | 2025-04-18 | 2025-05-30 | 5 | 22% | bar: WEEK 3 R to WEEK 4 W
2.1.2 | Negotiate costs | Monica M | 2025-04-21 | 2025-06-09 | 6 | 22% | bar: WEEK 3 F to WEEK 4 F
1 | Milestone: Contracts with suppliers | Monica M |  | 2025-06-09 | bar: WEEK 4 F
2.2 | Formulation development | Steve L | 2025-05-19 | 2025-07-14 | 9 | 22% | bar: WEEK 4 W to WEEK 6 M
2 | Milestone: Document with formula | Steve L |  | 2025-07-14 | bar: WEEK 6 M
3.1 | Product Testing | Steve L | 2025-06-09 | 2025-08-11 | 10 | 22% | bar: WEEK 4 F to WEEK 6 F
3 | Milestone: Testing approved | Steve L |  | 2025-08-11 | bar: WEEK 6 F
4.1 | Prototype refinement | Monica M | 2025-07-14 | 2025-09-05 | 7 | 22% | bar: WEEK 6 T to WEEK 7 W
4 | Milestone: protype refinement final document | Monica M |  | 2025-09-05 | bar: WEEK 7 W
3 | Brand Development & Packaging
3.1 | Brand identity | Pete S | 2025-04-21 | 2025-07-04 | 9 | 0% | bar: WEEK 3 F to WEEK 5 W
3.1.1 | Brand logo, name, brand message | Leon W | 2025-04-21 | 2025-07-04 | 9 | 0% | bar: WEEK 3 F to WEEK 5 W
1 | Milestone: Brand definition, message and logo | Leon W |  | 2025-07-04
3.2 | Packaging design | Kylie R | 2025-05-19 | 2025-08-15 | 12 | 0% | bar: WEEK 4 R to WEEK 6 F
3.2.1 | Check design | Kylie R | 2025-05-19 | 2025-08-15 | 12 | 0% | bar: WEEK 4 R to WEEK 6 F
3.2.2 | Packaging regulations | Pete S | 2025-05-19 | 2025-08-15 | 8 | 0% | bar: WEEK 4 R to WEEK 6 M
2 | Milestone: Document with packaging design to be printed | Pete S |  | 2025-08-15 | bar: WEEK 6 F
4 | Production & Manufacturing
4.1 | Contract Manufacturer Selection | Steve L | 2025-08-15 | 2025-10-23 | 10 | 0% | bar: WEEK 6 F to WEEK 8 F
1 | Milestone: Document with contract with manufacturer | Steve L |  | 2025-10-23 | bar: WEEK 8 F
4.2 | Production setup | Allen W | 2025-10-27 | 2025-03-16 | 20 | 0% | bar: WEEK 9 M to WEEK 12 R
2 | Milestone: 100 units | Allen W |  | 2025-12-08 | bar: WEEK 10 T
3 | Milestone:500 units | Allen W |  | 2026-03-16 | bar: WEEK 12 R
4.3 | Quality Control | Malik M | 2025-12-29 | 2026-04-27 | 20 | 0% | bar: WEEK 10 F to WEEK 14 M
4 | Milestone: Final document about Quality control | Malik M |  | 2026-04-27 | bar: WEEK 14 M
5 | Marketing & Distribution
5.1 | Marketing Strategy | Steve L | 2025-11-10 | 2026-03-30 | 20 | 0% | bar: WEEK 9 W to WEEK 13 T
5.1.1 | Marketing plan | Allen W | 2025-11-10 | 2026-02-02 | 12 | 0% | bar: WEEK 9 W to WEEK 11 R
5.1.2 | Promotional content | Malik M | 2026-03-19 | 2026-03-30 | 10 | 0% | bar: WEEK 11 W to WEEK 13 T
1 | Milestone: Marketing plan document | Malik M |  | 2026-03-30 | bar: WEEK 13 T
5.2 | Pre-launch & Launch campaign | Malik M | 2026-03-19 | 2026-08-27 | 23 | 0% | bar: WEEK 11 W to WEEK 15 F
2 | Milestone: Campaign document | Malik M |  | 2026-08-27 | bar: WEEK 15 F
6 | Post-Launch and Scaling
6.1 | Customer feedback | Steve L | 2026-07-09 | ongoing | 8 | 0% | bar: WEEK 14 W to WEEK 15 F
6.2 | Refinement and scaling | Allen W | 2026-07-09 | ongoing | 8 | 0% | bar: WEEK 14 W to WEEK 15 F
6.3 | Continuos marketing | Malik M | 2026-07-09 | ongoing | 8 | 0% | bar: WEEK 14 W to WEEK 15 F

## WORKS
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | MILESTONE 1 (website creation)
1.1 | Contract a web developer | Monica | 2018-03-12 | 2018-03-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | Monica | 2018-03-15 | 2018-03-16 | 1 | 100% | bar: WEEK 2 W
1.2 | Research | Monica | 2018-03-15 | 2018-03-21 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Projections | Monica | 2018-03-16 | 2018-03-22 | 6 | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Stakeholders | Monica | 2018-03-18 | 2018-03-22 | 4 | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 | Guidelines | Monica | 2018-03-19 | 2018-03-22 | 3 | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 | Project Initiation | Monica | 2018-03-23 | 2018-03-23 | 0 | 50% | bar: WEEK 3 F
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Steve L | 2018-03-24 | 2018-03-28 | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 | Budget | Allen W | 2018-03-29 | 2018-04-02 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | Communication Plan | Malik M |  |  | 0 | 0%
2.4 | Risk Management | Malik M |  |  | 0 | 0%
3 | Project Conception and Initiation
3.1 | Status and Tracking | Pete S |  |  | 0 | 0%
3.2 | KPIs | Leon W |  |  | 0 | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 | 0%
3.3 | Project Updates | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  | 0 | 0%
4.4 | Project Performance | Malik M |  |  | 0 | 0%